Project Management introduction – by Dr Richard-Nicolas LACROIX 30/4/2018

1) On youtube I found a very interesting video by Chris Croft, called "Project Management in under 8 minutes "

https://www.youtube.com/watch?v=qkuUBcmmBpk

this video presents just the "minimum 12 (twelve) essential" steps to getting started organizing an running a small /simple project (in reality you will need many hours of class work to learn this domain and it takes years to master this specialty as any other discipline like tennis or accounting) which are based on the simplified APM methodology from the Association of Project Managers in the UK (https://www.apm.org.uk/) .

2) Association of Project Managers (APM) 12-step Process - As per Chris Croft's Project Management in under 8 minutes (https://gist.github.com/gordonIanJ/5629928)

Step1: Define the project
- Cost (RNL: Budget)
- Quality (what)
- Time (when)
- Which is key driver: cost, quality, or time?
- Don't agree to a project you cannot deliver; don't say maybe
- Deliverable: Project Inititiation Document (PID)
- (RNL- Put the Project Requirements/ Constraints in Writing
PLANNING STEPS 2-8 BELOW
Step2: List the tasks
- Brainstorm a list
- Break the list into a Work Breakdown Structure (tree diagram of tasks)
- Consult an expert and/or history
- Deliverable: Work Breakdown Structure

Step3:Estimate the tasks
- Time
- Cost
- Don't promise the average. If you do: there's a fifty percent chance you'll fail to deliver. Better to promise "halfway between the average and the worst case"
- (RNL: Can Use CPM method to estimate duration based on probability)

Step4:Produce a Network Diagram aka Critical Path Diagram
- Find the longest path aka the critical path
- Heart of planning: this is where we decide how to actually "do" the project

Step5:"Crash" if necessary
- Cost up or quality down or both, for example
- Adjust the tasks on the critical path first; note whether floating tasks become critical as the critical path is shortened

Step6:Produce a Gantt Chart
- Put in the critical path first
- The floating tasks "hang off" the critical path
- The Gantt Chart is "brilliant" for three reasons
  - Each person can see his part of the project on the timeline
  - Can look vertically and see when you'll be busiest; calculate labor levels; slide floating tasks to reduce congestion
  - Can monitor by "coloring in"

Step7:Resource planning
- "Add up vertically"
- Perhaps even add up /all/ your projects; add up all "resource profiles"

Step8:Consider risk (what might go wrong?)
Consider how to make it less likely or less serious
GO BACK TO STEP ! TO NEGOTIATE IF YOU FEEL THE PROJECT IS UNACHIEVABLE

STEPS 9-12 ACTION:
Step9:Commit to the project or not
- Be assertive
- Use the Gantt Chart as an "arguing tool"

Step10:Monitor Progress
"Color in" the Gantt Chart

Step11:Monitor Finance
Combine with progress

Step12:Reschedule

NOTE on Project failures and need for an additional for these reasons:
## Four Main Problems of Project Management
1. Customer unhappy with Finished Result
  1. Avoid by defining in writing at the outset
2. Over Budget
  1. Avoid by
    1. Taking sufficient time to list tasks
    2. Getting every change signed for
    3. Estimating "halfway between the average and the worst case"
3. Late due to competing projects
  1. Make a Gantt of Gantts; "add up all resource profiles"; possibly only for your "bottleneck" resource
4. Late due to problems arising
  1. Avoid by having a risk plan with contingencies for both progress (time) and cost (money)
  2. Monitor progress, monitor cost; compare the two
5. All of the above
  1. Avoid by learning from previous projects by /doing a review/
  2. Store all project reviews for easy access

(Step13: Project Review:
- What was good?
- What was bad?
- What could we have done better?
)

3) Dilbert Visionary Leadership (Humour on Project Management)
https://www.youtube.com/watch?v=7Rv1_Srn-T4&list=PLHIvsxgJ17w7YTcI4LjPusMtN16oL5Zyx&index=3

4) Class Notes Richard LACROIX for MSProject 2003 in Greek

https://drive.google.com/open?id=0B6C2pPcND_HOSXdfNW1jUDVtUVk

5) Presentation National School of Public Administration for teaching Project Management for Managers / Directors in Greek Public Administration.

https://drive.google.com/open?id=0B6C2pPcND_HObjEtM192ZmZhYnc